## Simulation
Aventis
Simulation Info
Name | XX
Vessel Name | Test Vessel
Scope | Test Scope
Project | Project ID
Simulation ID | Name as you like
More Information | Some more info (Not used in simulation)
Options
ID | Name as you like
Default Weather data | X1
Simulation Type (Set Start/ Set End/ Date Range) | Set Start
Input Date | 2023-06-01 | [7 empty] | Set Start
Input Date 2 (Only needed for Date Range)
WTG Properties File | filepath to wtg properties file /Projects - Documents/CNS - Expert Consultancy/P-CNS-ITK-44721-Metocean and Installation Analysis Support/WP2 - Tender Analysis/Weather Data/01 WTG Properties Aventis/Location Properties.xlsx
Transit Speed [kts] | 0
Intra-Site Transit Speed [kts] | 0
Shift Pattern
24 Hour | Yes
Shift Start [HH:MM] | 6:00
Shift End [HH:MM] | 18:00
Transit Duration [HH:MM] | 1:00
Sequence
Sequence Implemented | No
Activity that Marks Start of Location | Milestone: End Survey Block
Activity that Marks End of Location | Milestone: End Survey Block
Linked Simulation
Linked Simulation (Yes/ No) | No
Previous Simulation or Set Dates | filepath to previous simulation
Linked Activity (Previous Simulation) | Milestone: Permit Ready
Linked Activity (Current Simulation) | Wait for Permit
Output
Export Stats | Yes
Plot Plume | Yes
Metocean WDT | Yes
Activity WDT | No
Compare with Programme | Yes
Save Files | Yes | [22 empty] | Location classified by code with the following rules
Space for Further Options | Space for further Options | [22 empty] | Transit - activity name starts with "Transit to"
WTG ID - read from sequence between activities in Sequence Options
Weather | [23 empty] | Port - weather file is port
ID | filepath | [22 empty] | Undefined - does not satisfy any of the above
weather_file_1 | filepath to weather pickle or csv /Users/jontypedersen/Library/CloudStorage/OneDrive-SharedLibraries-ODSL/Projects - Documents/Python Utilities/13 Aventis/Aventis/Demo/Weather and Properties/Demo_Weather_data.csv
Workflow | [8 empty] | Operability Limits
Activity | Cycles | Net Duration [hrs] | Minimum Window Duration [hrs] | Parallel | Limit Activity | Parallel Duration [hrs] | Data utilised | Continuous | Parameter | < > = | Value | and | Parameter | < > = | Value | and | Parameter | < > = | Value | and | Parameter | < > = | Value
Offshore Geophys | 1
Offshore Geotech | 1
Offshore Benthic | 1
Offshore Geophys | 1
Offshore ROV Crossing | 1
Fragnets
FRAGNET: Offshore Geophys
Milestone: Start Survey | 1 | 0 | 1 |  |  |  | weather_file_1
Mobs and Cals | 1 | 24 | 24 |  |  |  | weather_file_1
Geophys Survey 1 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2 |  | WS10_10m | < | 12.5
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Geophys Survey 2 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2.5 |  | WS10_10m | < | 12.5
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Geophys Survey 3 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 3 |  | WS10_10m | < | 15
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Geophys Survey 4 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2 |  | WS10_10m | < | 20
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Geophys Survey 5 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2.5 |  | WS10_10m | < | 36
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Demob | 1 | 24 | 24 |  |  |  | weather_file_1
FRAGNET: Offshore Geotech
Mobs and Cals (Geotech Interim) | 1 | 36 | 36 |  |  |  | weather_file_1
Geotech Survey 1 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2 |  | WS10_10m | < | 12.5
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Geotech Survey 2 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2.5 |  | WS10_10m | < | 12.5
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Geotech Survey 3 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 3 |  | WS10_10m | < | 15
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Geotech Survey 4 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2 |  | WS10_10m | < | 20
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Geotech Survey 5 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2.5 |  | WS10_10m | < | 36
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Demob (Geotech Interim) | 1 | 24 | 24 |  |  |  | weather_file_1
FRAGNET: Offshore Benthic
Mobs and Cals (Benthic Interim) | 1 | 24 | 24 |  |  |  | weather_file_1
Benthic Survey 1 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2 |  | WS10_10m | < | 12.5
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Benthic Survey 2 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2.5 |  | WS10_10m | < | 12.5
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Benthic Survey 3 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 3 |  | WS10_10m | < | 15
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Benthic Survey 4 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2 |  | WS10_10m | < | 20
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Benthic Survey 5 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2.5 |  | WS10_10m | < | 36
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Demob (Benthic Interim) | 1 | 24 | 24 |  |  |  | weather_file_1
FRAGNET: Offshore ROV Crossing
Mobs and Cals (ROV Interim) | 1 | 24 | 24 |  |  |  | weather_file_1
ROV Survey 1 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2 |  | WS10_10m | < | 12.5 |  | Tp | < | 7
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
ROV Survey 2 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2.5 |  | WS10_10m | < | 12.5 |  | Tp | < | 7
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
ROV Survey 3 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 3 |  | WS10_10m | < | 15 |  | Tp | < | 7
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
ROV Survey 4 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2 |  | WS10_10m | < | 20 |  | Tp | < | 8
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
ROV Survey 5 | 1 | 24 | 24 |  |  |  | weather_file_1 |  | Hs | < | 2.5 |  | WS10_10m | < | 36 |  | Tp | < | 8
Milestone: End Survey Block | 1 | 0 | 1 |  |  |  | weather_file_1
Demob Final (ROV) | 1 | 24 | 24 |  |  |  | weather_file_1
Milestone: Finish Survey | 1 | 0 | 1 |  |  |  | weather_file_1
Note on D55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If a “Transit to” from or to site and using transit speed, then net duration turns in to net distance in km.

## Programme
Programme
% | End Date | % | End Date
Tenderer P0 | Tenderer P0 | Tenderer P80 | Tenderer P80

## Lists (hidden)
Yes | Set Start
No | Date Range

## weather_file_1
Parameters Present |  |  | Inputs |  | Derived Parameter |  | Derived Boolean Vector
SiteID | Type | Unit | Years | Year Value | DP ID | DP Formula | DB ID | Parameters | Param Limits
|  |  | Years Used | all
Hs |  | m | Start Date
Tp |  | s | End Date
WS10_10m |  | m/s

## Sequence
Sequence
Simulation Sequence ID | Conditioning Simulation Sequence | Date | Days Float | Notes
|  | 2019-10-01 | 0 | Date of completion of previous simulation (optional as it can be read from previous simulation)
|  | 2019-10-01 | 0 | Days float is days float required between conditioned and conditioning activity
|  | 2019-10-01 | 0 | Simulation Sequence is the sequnce of the current simulation
|  | 2019-10-01 | 0 | Conditioned sequence ID is the simulation of the conditioned simulation (optional as it can be read from the previous sim)
|  | 2019-10-01 | 0
|  | 2019-10-01 | 0
|  | 2019-10-01 | 0
|  | 2019-10-01 | 0
|  | 2019-10-01 | 0
|  | 2019-10-01 | 0
|  | 2019-10-01 | 0
|  | 2019-10-01 | 0
|  | 2019-10-01 | 0
|  | 2019-10-01 | 0
|  | 2019-10-01 | 0