## Summary
Summary of downtimes
Options
Simulation ID | Name as you like
Simulation Type | Set Start
Start Date | 2023-06-01
Work Shift | 24 Hours
Linked Simulation | filepath to previous simulation
Downtime Type | P0 | P10 | P20 | P30 | P40 | P50 | P60 | P70 | P80 | P90 | P100
Total duration [days] | 35.5 | 37 | 37 | 37 | 38 | 38 | 38 | 38.8 | 39 | 39 | 40
Shift downtime [days] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weather downtime & Stand by [days] | 0 | 1.5 | 1.5 | 1.5 | 2.5 | 2.5 | 2.5 | 3.3 | 3.5 | 3.5 | 4.5
End date | 2023-07-06 12:00 | 2023-07-07 23:00 | 2023-07-07 23:00 | 2023-07-08 | 2023-07-08 23:00 | 2023-07-08 23:30 | 2023-07-08 23:30 | 2023-07-09 20:00 | 2023-07-09 23:00 | 2023-07-09 23:00 | 2023-07-10 23:30
Year | filepath to previous simulation P0: P0 duration [days]; filepath to previous simulation P10: Total duration [days]; filepath to previous simulation P20: Additional shift downtime [days]; filepath to previous simulation P30: Stand by for pre-requisite activity [days]; filepath to previous simulation P40: Weather Downtime [days]
1979 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37.9792; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.4792
1980 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 36.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 1.4583
1981 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37.9792; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.4792
1982 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 36.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 1.4583
1983 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 36.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 1.4583
1984 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 38.8333; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 3.3333
1985 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 35.5; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 0
1986 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 38.9792; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 3.4792
1987 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 38.25; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.75
1988 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 38.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 3.4583
1989 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.4583
1990 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 38.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 3.4583
1991 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.4583
1992 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 35.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 0.45833
1993 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37.625; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.125
1994 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 1.5
1995 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 38.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 3.4583
1996 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 38.7917; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 3.2917
1997 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 1.5
1998 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 38.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 3.4583
1999 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 39.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 4.4583
2000 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 38.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 3.4583
2001 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 36.1667; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 0.66667
2002 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 38.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 3.4583
2003 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.4583
2004 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 39.9792; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 4.4792
2005 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 38.9792; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 3.4792
2006 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.4583
2007 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37.75; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.25
2008 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37.9792; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.4792
2009 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37.9792; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.4792
2010 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 35.5; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 0
2011 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37.9792; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.4792
2012 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 36.9792; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 1.4792
2013 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 38.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 3.4583
2014 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 36.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 1.4583
2015 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 36.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 1.4583
2016 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37.9792; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.4792
2017 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 37.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 2.4583
2018 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 38.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 3.4583
2019 | filepath to previous simulation P0: 35.5; filepath to previous simulation P10: 36.9583; filepath to previous simulation P20: 0; filepath to previous simulation P30: 0; filepath to previous simulation P40: 1.4583

## Workability
Workability of activities
Months | Geophys Survey 1 | Geophys Survey 2 | Geophys Survey 3 | Geophys Survey 4 | Geophys Survey 5 | Geotech Survey 1 | Geotech Survey 2 | Geotech Survey 3 | Geotech Survey 4 | Geotech Survey 5 | Benthic Survey 1 | Benthic Survey 2 | Benthic Survey 3 | Benthic Survey 4 | Benthic Survey 5 | ROV Survey 1 | ROV Survey 2 | ROV Survey 3 | ROV Survey 4 | ROV Survey 5
Jan | 86.6% | 96.6% | 99.2% | 86.6% | 96.6% | 86.6% | 96.6% | 99.2% | 86.6% | 96.6% | 86.6% | 96.6% | 99.2% | 86.6% | 96.6% | 40.1% | 40.1% | 40.1% | 67% | 68.8%
Feb | 93.6% | 98.2% | 99.5% | 93.6% | 98.2% | 93.6% | 98.2% | 99.5% | 93.6% | 98.2% | 93.6% | 98.2% | 99.5% | 93.6% | 98.2% | 55.2% | 55.2% | 55.2% | 80.6% | 80.9%
Mar | 96.4% | 99.3% | 99.8% | 96.4% | 99.3% | 96.4% | 99.3% | 99.8% | 96.4% | 99.3% | 96.4% | 99.3% | 99.8% | 96.4% | 99.3% | 67.1% | 67.1% | 67.1% | 86.4% | 86.5%
Apr | 97.2% | 99.4% | 100% | 97.2% | 99.4% | 97.2% | 99.4% | 100% | 97.2% | 99.4% | 97.2% | 99.4% | 100% | 97.2% | 99.4% | 76.6% | 76.6% | 76.6% | 87.7% | 88%
May | 97.5% | 99.2% | 99.9% | 97.5% | 99.2% | 97.5% | 99.2% | 99.9% | 97.5% | 99.2% | 97.5% | 99.2% | 99.9% | 97.5% | 99.2% | 81.6% | 81.6% | 81.6% | 89.3% | 89.5%
Jun | 96.9% | 98.9% | 99.6% | 96.9% | 98.9% | 96.9% | 98.9% | 99.6% | 96.9% | 98.9% | 96.9% | 98.9% | 99.6% | 96.9% | 98.9% | 82.8% | 82.8% | 82.8% | 90.1% | 90.8%
Jul | 96.9% | 98.7% | 99.5% | 96.9% | 98.7% | 96.9% | 98.7% | 99.5% | 96.9% | 98.7% | 96.9% | 98.7% | 99.5% | 96.9% | 98.7% | 81.8% | 81.8% | 81.8% | 90.1% | 90.3%
Aug | 97.3% | 98.9% | 99.7% | 97.3% | 98.9% | 97.3% | 98.9% | 99.7% | 97.3% | 98.9% | 97.3% | 98.9% | 99.7% | 97.3% | 98.9% | 80.3% | 80.3% | 80.3% | 90% | 90.2%
Sep | 97% | 99.3% | 100% | 97% | 99.3% | 97% | 99.3% | 100% | 97% | 99.3% | 97% | 99.3% | 100% | 97% | 99.3% | 79% | 79% | 79% | 88.1% | 88.6%
Oct | 96.9% | 99.3% | 99.9% | 96.9% | 99.4% | 96.9% | 99.3% | 99.9% | 96.9% | 99.4% | 96.9% | 99.3% | 99.9% | 96.9% | 99.4% | 56.9% | 57% | 57.1% | 71.4% | 72.4%
Nov | 91.3% | 97.8% | 99.6% | 91.3% | 97.8% | 91.3% | 97.8% | 99.6% | 91.3% | 97.8% | 91.3% | 97.8% | 99.6% | 91.3% | 97.8% | 48% | 48% | 48% | 68.8% | 69.9%
Dec | 82.8% | 94.3% | 98.6% | 82.8% | 94.4% | 82.8% | 94.3% | 98.6% | 82.8% | 94.4% | 82.8% | 94.3% | 98.6% | 82.8% | 94.4% | 35.2% | 35.2% | 35.2% | 60.7% | 63.3%

## Cause of WDT
Weather parameters that caused WDT
Activity | Hs | WS10_10m | Tp
Benthic Survey 1 | 0 | 0 | 0
Benthic Survey 2 | 0 | 0 | 0
Benthic Survey 3 | 0 | 0 | 0
Benthic Survey 4 | 0 | 0 | 0
Benthic Survey 5 | 0 | 0 | 0
Demob | 0 | 0 | 0
Demob (Benthic Interim) | 0 | 0 | 0
Demob (Geotech Interim) | 0 | 0 | 0
Demob Final (ROV) | 0 | 0 | 0
Geophys Survey 1 | 5.7317 | 0 | 0
Geophys Survey 2 | 0 | 0 | 0
Geophys Survey 3 | 0 | 0 | 0
Geophys Survey 4 | 0 | 0 | 0
Geophys Survey 5 | 0 | 0 | 0
Geotech Survey 1 | 0 | 0 | 0
Geotech Survey 2 | 0 | 0 | 0
Geotech Survey 3 | 0 | 0 | 0
Geotech Survey 4 | 2 | 0 | 0
Geotech Survey 5 | 0 | 0 | 0
Milestone: End Survey Block | 0 | 0 | 0
Milestone: Finish Survey | 0 | 0 | 0
Milestone: Start Survey | 0 | 0 | 0
Mobs and Cals | 0 | 0 | 0
Mobs and Cals (Benthic Interim) | 0 | 0 | 0
Mobs and Cals (Geotech Interim) | 0 | 0 | 0
Mobs and Cals (ROV Interim) | 0 | 0 | 0
ROV Survey 1 | 10.4878 | 0.82927 | 63.0244
ROV Survey 2 | 0 | 0 | 8.3171
ROV Survey 3 | 0 | 0 | 2.2195
ROV Survey 4 | 0 | 0 | 1.2683
ROV Survey 5 | 0 | 0 | 0

## Activity Completion Dates
Percentile start and end datetimes for each activity
Location | AC | Start P0 | Start P10 | Start P20 | Start P30 | Start P40 | Start P50 | Start P60 | Start P70 | Start P80 | Start P90 | Start P100 | End P0 | End P10 | End P20 | End P30 | End P40 | End P50 | End P60 | End P70 | End P80 | End P90 | End P100
Undefined | Milestone: Start Survey | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01
Undefined | Mobs and Cals | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02
Undefined | Geophys Survey 1 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 02:00 | 2023-06-03 21:00 | 2023-06-04 23:00
Undefined | Milestone: End Survey Block | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 02:00 | 2023-06-03 21:00 | 2023-06-04 23:00 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 02:00 | 2023-06-03 21:00 | 2023-06-04 23:00
Undefined | Geophys Survey 2 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 02:00 | 2023-06-03 21:00 | 2023-06-04 23:00 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 02:00 | 2023-06-04 21:00 | 2023-06-05 23:00
Undefined | Milestone: End Survey Block | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 02:00 | 2023-06-04 21:00 | 2023-06-05 23:00 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 02:00 | 2023-06-04 21:00 | 2023-06-05 23:00
Undefined | Geophys Survey 3 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 | 2023-06-04 02:00 | 2023-06-04 21:00 | 2023-06-05 23:00 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 02:00 | 2023-06-05 21:00 | 2023-06-06 23:00
Undefined | Milestone: End Survey Block | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 02:00 | 2023-06-05 21:00 | 2023-06-06 23:00 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 02:00 | 2023-06-05 21:00 | 2023-06-06 23:00
Undefined | Geophys Survey 4 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 02:00 | 2023-06-05 21:00 | 2023-06-06 23:00 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 02:00 | 2023-06-06 21:00 | 2023-06-07 23:00
Undefined | Milestone: End Survey Block | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 02:00 | 2023-06-06 21:00 | 2023-06-07 23:00 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 02:00 | 2023-06-06 21:00 | 2023-06-07 23:00
Undefined | Geophys Survey 5 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-06 02:00 | 2023-06-06 21:00 | 2023-06-07 23:00 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 02:00 | 2023-06-07 21:00 | 2023-06-08 23:00
Undefined | Milestone: End Survey Block | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 02:00 | 2023-06-07 21:00 | 2023-06-08 23:00 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 02:00 | 2023-06-07 21:00 | 2023-06-08 23:00
Undefined | Demob | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 02:00 | 2023-06-07 21:00 | 2023-06-08 23:00 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 02:00 | 2023-06-08 21:00 | 2023-06-09 23:00
Undefined | Mobs and Cals (Geotech Interim) | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 02:00 | 2023-06-08 21:00 | 2023-06-09 23:00 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 14:00 | 2023-06-10 09:00 | 2023-06-11 11:00
Undefined | Geotech Survey 1 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 12:00 | 2023-06-09 14:00 | 2023-06-10 09:00 | 2023-06-11 11:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 14:00 | 2023-06-11 09:00 | 2023-06-12 11:00
Undefined | Milestone: End Survey Block | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 14:00 | 2023-06-11 09:00 | 2023-06-12 11:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 14:00 | 2023-06-11 09:00 | 2023-06-12 11:00
Undefined | Geotech Survey 2 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 12:00 | 2023-06-10 14:00 | 2023-06-11 09:00 | 2023-06-12 11:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 14:00 | 2023-06-12 09:00 | 2023-06-13 11:00
Undefined | Milestone: End Survey Block | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 14:00 | 2023-06-12 09:00 | 2023-06-13 11:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 14:00 | 2023-06-12 09:00 | 2023-06-13 11:00
Undefined | Geotech Survey 3 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 12:00 | 2023-06-11 14:00 | 2023-06-12 09:00 | 2023-06-13 11:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 14:00 | 2023-06-13 09:00 | 2023-06-14 11:00
Undefined | Milestone: End Survey Block | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 14:00 | 2023-06-13 09:00 | 2023-06-14 11:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 14:00 | 2023-06-13 09:00 | 2023-06-14 11:00
Undefined | Geotech Survey 4 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 12:00 | 2023-06-12 14:00 | 2023-06-13 09:00 | 2023-06-14 11:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 16:00 | 2023-06-13 23:00 | 2023-06-14 09:00 | 2023-06-15 11:00
Undefined | Milestone: End Survey Block | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 16:00 | 2023-06-13 23:00 | 2023-06-14 09:00 | 2023-06-15 11:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 16:00 | 2023-06-13 23:00 | 2023-06-14 09:00 | 2023-06-15 11:00
Undefined | Geotech Survey 5 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 12:00 | 2023-06-13 16:00 | 2023-06-13 23:00 | 2023-06-14 09:00 | 2023-06-15 11:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 16:00 | 2023-06-14 23:00 | 2023-06-15 09:00 | 2023-06-16 11:00
Undefined | Milestone: End Survey Block | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 16:00 | 2023-06-14 23:00 | 2023-06-15 09:00 | 2023-06-16 11:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 16:00 | 2023-06-14 23:00 | 2023-06-15 09:00 | 2023-06-16 11:00
Undefined | Demob (Geotech Interim) | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 12:00 | 2023-06-14 16:00 | 2023-06-14 23:00 | 2023-06-15 09:00 | 2023-06-16 11:00 | 2023-06-15 12:00 | 2023-06-15 12:00 | 2023-06-15 12:00 | 2023-06-15 12:00 | 2023-06-15 12:00 | 2023-06-15 12:00 | 2023-06-15 12:00 | 2023-06-15 16:00 | 2023-06-15 23:00 | 2023-06-16 09:00 | 2023-06-17 11:00
Undefined | Mobs and Cals (Benthic Interim) | 2023-06-15 12:00 | 2023-06-15 12:00 | 2023-06-15 12:00 | 2023-06-15 12:00 | 2023-06-15 12:00 | 2023-06-15 12:00 | 2023-06-15 12:00 | 2023-06-15 16:00 | 2023-06-15 23:00 | 2023-06-16 09:00 | 2023-06-17 11:00 | 2023-06-16 12:00 | 2023-06-16 12:00 | 2023-06-16 12:00 | 2023-06-16 12:00 | 2023-06-16 12:00 | 2023-06-16 12:00 | 2023-06-16 12:00 | 2023-06-16 16:00 | 2023-06-16 23:00 | 2023-06-17 09:00 | 2023-06-18 11:00
Undefined | Benthic Survey 1 | 2023-06-16 12:00 | 2023-06-16 12:00 | 2023-06-16 12:00 | 2023-06-16 12:00 | 2023-06-16 12:00 | 2023-06-16 12:00 | 2023-06-16 12:00 | 2023-06-16 16:00 | 2023-06-16 23:00 | 2023-06-17 09:00 | 2023-06-18 11:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 16:00 | 2023-06-17 23:00 | 2023-06-18 09:00 | 2023-06-19 11:00
Undefined | Milestone: End Survey Block | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 16:00 | 2023-06-17 23:00 | 2023-06-18 09:00 | 2023-06-19 11:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 16:00 | 2023-06-17 23:00 | 2023-06-18 09:00 | 2023-06-19 11:00
Undefined | Benthic Survey 2 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 12:00 | 2023-06-17 16:00 | 2023-06-17 23:00 | 2023-06-18 09:00 | 2023-06-19 11:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 16:00 | 2023-06-18 23:00 | 2023-06-19 09:00 | 2023-06-20 11:00
Undefined | Milestone: End Survey Block | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 16:00 | 2023-06-18 23:00 | 2023-06-19 09:00 | 2023-06-20 11:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 16:00 | 2023-06-18 23:00 | 2023-06-19 09:00 | 2023-06-20 11:00
Undefined | Benthic Survey 3 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 12:00 | 2023-06-18 16:00 | 2023-06-18 23:00 | 2023-06-19 09:00 | 2023-06-20 11:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 16:00 | 2023-06-19 23:00 | 2023-06-20 09:00 | 2023-06-21 11:00
Undefined | Milestone: End Survey Block | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 16:00 | 2023-06-19 23:00 | 2023-06-20 09:00 | 2023-06-21 11:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 16:00 | 2023-06-19 23:00 | 2023-06-20 09:00 | 2023-06-21 11:00
Undefined | Benthic Survey 4 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 12:00 | 2023-06-19 16:00 | 2023-06-19 23:00 | 2023-06-20 09:00 | 2023-06-21 11:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 16:00 | 2023-06-20 23:00 | 2023-06-21 09:00 | 2023-06-22 11:00
Undefined | Milestone: End Survey Block | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 16:00 | 2023-06-20 23:00 | 2023-06-21 09:00 | 2023-06-22 11:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 16:00 | 2023-06-20 23:00 | 2023-06-21 09:00 | 2023-06-22 11:00
Undefined | Benthic Survey 5 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 12:00 | 2023-06-20 16:00 | 2023-06-20 23:00 | 2023-06-21 09:00 | 2023-06-22 11:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 16:00 | 2023-06-21 23:00 | 2023-06-22 09:00 | 2023-06-23 11:00
Undefined | Milestone: End Survey Block | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 16:00 | 2023-06-21 23:00 | 2023-06-22 09:00 | 2023-06-23 11:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 16:00 | 2023-06-21 23:00 | 2023-06-22 09:00 | 2023-06-23 11:00
Undefined | Demob (Benthic Interim) | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 12:00 | 2023-06-21 16:00 | 2023-06-21 23:00 | 2023-06-22 09:00 | 2023-06-23 11:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 16:00 | 2023-06-22 23:00 | 2023-06-23 09:00 | 2023-06-24 11:00
Undefined | Milestone: Start Survey | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 16:00 | 2023-06-22 23:00 | 2023-06-23 09:00 | 2023-06-24 11:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 16:00 | 2023-06-22 23:00 | 2023-06-23 09:00 | 2023-06-24 11:00
Undefined | Mobs and Cals | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 12:00 | 2023-06-22 16:00 | 2023-06-22 23:00 | 2023-06-23 09:00 | 2023-06-24 11:00 | 2023-06-23 12:00 | 2023-06-23 12:00 | 2023-06-23 12:00 | 2023-06-23 12:00 | 2023-06-23 12:00 | 2023-06-23 12:00 | 2023-06-23 12:00 | 2023-06-23 16:00 | 2023-06-23 23:00 | 2023-06-24 09:00 | 2023-06-25 11:00
Undefined | Geophys Survey 1 | 2023-06-23 12:00 | 2023-06-23 12:00 | 2023-06-23 12:00 | 2023-06-23 12:00 | 2023-06-23 12:00 | 2023-06-23 12:00 | 2023-06-23 12:00 | 2023-06-23 16:00 | 2023-06-23 23:00 | 2023-06-24 09:00 | 2023-06-25 11:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 16:00 | 2023-06-24 23:00 | 2023-06-25 09:00 | 2023-06-26 11:00
Undefined | Milestone: End Survey Block | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 16:00 | 2023-06-24 23:00 | 2023-06-25 09:00 | 2023-06-26 11:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 16:00 | 2023-06-24 23:00 | 2023-06-25 09:00 | 2023-06-26 11:00
Undefined | Geophys Survey 2 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 12:00 | 2023-06-24 16:00 | 2023-06-24 23:00 | 2023-06-25 09:00 | 2023-06-26 11:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 16:00 | 2023-06-25 23:00 | 2023-06-26 09:00 | 2023-06-27 11:00
Undefined | Milestone: End Survey Block | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 16:00 | 2023-06-25 23:00 | 2023-06-26 09:00 | 2023-06-27 11:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 16:00 | 2023-06-25 23:00 | 2023-06-26 09:00 | 2023-06-27 11:00
Undefined | Geophys Survey 3 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 12:00 | 2023-06-25 16:00 | 2023-06-25 23:00 | 2023-06-26 09:00 | 2023-06-27 11:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 16:00 | 2023-06-26 23:00 | 2023-06-27 09:00 | 2023-06-28 11:00
Undefined | Milestone: End Survey Block | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 16:00 | 2023-06-26 23:00 | 2023-06-27 09:00 | 2023-06-28 11:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 16:00 | 2023-06-26 23:00 | 2023-06-27 09:00 | 2023-06-28 11:00
Undefined | Geophys Survey 4 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 12:00 | 2023-06-26 16:00 | 2023-06-26 23:00 | 2023-06-27 09:00 | 2023-06-28 11:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 16:00 | 2023-06-27 23:00 | 2023-06-28 09:00 | 2023-06-29 11:00
Undefined | Milestone: End Survey Block | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 16:00 | 2023-06-27 23:00 | 2023-06-28 09:00 | 2023-06-29 11:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 16:00 | 2023-06-27 23:00 | 2023-06-28 09:00 | 2023-06-29 11:00
Undefined | Geophys Survey 5 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 12:00 | 2023-06-27 16:00 | 2023-06-27 23:00 | 2023-06-28 09:00 | 2023-06-29 11:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 16:00 | 2023-06-28 23:00 | 2023-06-29 09:00 | 2023-06-30 11:00
Undefined | Milestone: End Survey Block | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 16:00 | 2023-06-28 23:00 | 2023-06-29 09:00 | 2023-06-30 11:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 16:00 | 2023-06-28 23:00 | 2023-06-29 09:00 | 2023-06-30 11:00
Undefined | Demob | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 12:00 | 2023-06-28 16:00 | 2023-06-28 23:00 | 2023-06-29 09:00 | 2023-06-30 11:00 | 2023-06-29 12:00 | 2023-06-29 12:00 | 2023-06-29 12:00 | 2023-06-29 12:00 | 2023-06-29 12:00 | 2023-06-29 12:00 | 2023-06-29 12:00 | 2023-06-29 16:00 | 2023-06-29 23:00 | 2023-06-30 09:00 | 2023-07-01 11:00
Undefined | Mobs and Cals (ROV Interim) | 2023-06-29 12:00 | 2023-06-29 12:00 | 2023-06-29 12:00 | 2023-06-29 12:00 | 2023-06-29 12:00 | 2023-06-29 12:00 | 2023-06-29 12:00 | 2023-06-29 16:00 | 2023-06-29 23:00 | 2023-06-30 09:00 | 2023-07-01 11:00 | 2023-06-30 12:00 | 2023-06-30 12:00 | 2023-06-30 12:00 | 2023-06-30 12:00 | 2023-06-30 12:00 | 2023-06-30 12:00 | 2023-06-30 12:00 | 2023-06-30 16:00 | 2023-06-30 23:00 | 2023-07-01 09:00 | 2023-07-02 11:00
Undefined | ROV Survey 1 | 2023-06-30 12:00 | 2023-06-30 12:00 | 2023-06-30 12:00 | 2023-06-30 12:00 | 2023-06-30 12:00 | 2023-06-30 12:00 | 2023-06-30 12:00 | 2023-06-30 16:00 | 2023-06-30 23:00 | 2023-07-01 09:00 | 2023-07-02 11:00 | 2023-07-01 12:00 | 2023-07-01 12:00 | 2023-07-02 23:00 | 2023-07-02 23:00 | 2023-07-02 23:30 | 2023-07-03 23:00 | 2023-07-03 23:30 | 2023-07-03 23:30 | 2023-07-04 19:00 | 2023-07-04 23:00 | 2023-07-05 23:30
Undefined | Milestone: End Survey Block | 2023-07-01 12:00 | 2023-07-01 12:00 | 2023-07-02 23:00 | 2023-07-02 23:00 | 2023-07-02 23:30 | 2023-07-03 23:00 | 2023-07-03 23:30 | 2023-07-03 23:30 | 2023-07-04 19:00 | 2023-07-04 23:00 | 2023-07-05 23:30 | 2023-07-01 12:00 | 2023-07-01 12:00 | 2023-07-02 23:00 | 2023-07-02 23:00 | 2023-07-02 23:30 | 2023-07-03 23:00 | 2023-07-03 23:30 | 2023-07-03 23:30 | 2023-07-04 19:00 | 2023-07-04 23:00 | 2023-07-05 23:30
Undefined | ROV Survey 2 | 2023-07-01 12:00 | 2023-07-01 12:00 | 2023-07-02 23:00 | 2023-07-02 23:00 | 2023-07-02 23:30 | 2023-07-03 23:00 | 2023-07-03 23:30 | 2023-07-03 23:30 | 2023-07-04 19:00 | 2023-07-04 23:00 | 2023-07-05 23:30 | 2023-07-02 12:00 | 2023-07-02 23:00 | 2023-07-03 23:00 | 2023-07-03 23:30 | 2023-07-04 23:00 | 2023-07-04 23:00 | 2023-07-04 23:30 | 2023-07-05 06:00 | 2023-07-05 23:00 | 2023-07-05 23:00 | 2023-07-06 23:30
Undefined | Milestone: End Survey Block | 2023-07-02 12:00 | 2023-07-02 23:00 | 2023-07-03 23:00 | 2023-07-03 23:30 | 2023-07-04 23:00 | 2023-07-04 23:00 | 2023-07-04 23:30 | 2023-07-05 06:00 | 2023-07-05 23:00 | 2023-07-05 23:00 | 2023-07-06 23:30 | 2023-07-02 12:00 | 2023-07-02 23:00 | 2023-07-03 23:00 | 2023-07-03 23:30 | 2023-07-04 23:00 | 2023-07-04 23:00 | 2023-07-04 23:30 | 2023-07-05 06:00 | 2023-07-05 23:00 | 2023-07-05 23:00 | 2023-07-06 23:30
Undefined | ROV Survey 3 | 2023-07-02 12:00 | 2023-07-02 23:00 | 2023-07-03 23:00 | 2023-07-03 23:30 | 2023-07-04 23:00 | 2023-07-04 23:00 | 2023-07-04 23:30 | 2023-07-05 06:00 | 2023-07-05 23:00 | 2023-07-05 23:00 | 2023-07-06 23:30 | 2023-07-03 12:00 | 2023-07-04 23:00 | 2023-07-04 23:00 | 2023-07-05 | 2023-07-05 23:00 | 2023-07-05 23:00 | 2023-07-05 23:30 | 2023-07-06 19:00 | 2023-07-06 23:00 | 2023-07-06 23:00 | 2023-07-07 23:30
Undefined | Milestone: End Survey Block | 2023-07-03 12:00 | 2023-07-04 23:00 | 2023-07-04 23:00 | 2023-07-05 | 2023-07-05 23:00 | 2023-07-05 23:00 | 2023-07-05 23:30 | 2023-07-06 19:00 | 2023-07-06 23:00 | 2023-07-06 23:00 | 2023-07-07 23:30 | 2023-07-03 12:00 | 2023-07-04 23:00 | 2023-07-04 23:00 | 2023-07-05 | 2023-07-05 23:00 | 2023-07-05 23:00 | 2023-07-05 23:30 | 2023-07-06 19:00 | 2023-07-06 23:00 | 2023-07-06 23:00 | 2023-07-07 23:30
Undefined | ROV Survey 4 | 2023-07-03 12:00 | 2023-07-04 23:00 | 2023-07-04 23:00 | 2023-07-05 | 2023-07-05 23:00 | 2023-07-05 23:00 | 2023-07-05 23:30 | 2023-07-06 19:00 | 2023-07-06 23:00 | 2023-07-06 23:00 | 2023-07-07 23:30 | 2023-07-04 12:00 | 2023-07-05 23:00 | 2023-07-05 23:00 | 2023-07-06 | 2023-07-06 23:00 | 2023-07-06 23:30 | 2023-07-06 23:30 | 2023-07-07 20:00 | 2023-07-07 23:00 | 2023-07-07 23:00 | 2023-07-08 23:30
Undefined | Milestone: End Survey Block | 2023-07-04 12:00 | 2023-07-05 23:00 | 2023-07-05 23:00 | 2023-07-06 | 2023-07-06 23:00 | 2023-07-06 23:30 | 2023-07-06 23:30 | 2023-07-07 20:00 | 2023-07-07 23:00 | 2023-07-07 23:00 | 2023-07-08 23:30 | 2023-07-04 12:00 | 2023-07-05 23:00 | 2023-07-05 23:00 | 2023-07-06 | 2023-07-06 23:00 | 2023-07-06 23:30 | 2023-07-06 23:30 | 2023-07-07 20:00 | 2023-07-07 23:00 | 2023-07-07 23:00 | 2023-07-08 23:30
Undefined | ROV Survey 5 | 2023-07-04 12:00 | 2023-07-05 23:00 | 2023-07-05 23:00 | 2023-07-06 | 2023-07-06 23:00 | 2023-07-06 23:30 | 2023-07-06 23:30 | 2023-07-07 20:00 | 2023-07-07 23:00 | 2023-07-07 23:00 | 2023-07-08 23:30 | 2023-07-05 12:00 | 2023-07-06 23:00 | 2023-07-06 23:00 | 2023-07-07 | 2023-07-07 23:00 | 2023-07-07 23:30 | 2023-07-07 23:30 | 2023-07-08 20:00 | 2023-07-08 23:00 | 2023-07-08 23:00 | 2023-07-09 23:30
Undefined | Milestone: End Survey Block | 2023-07-05 12:00 | 2023-07-06 23:00 | 2023-07-06 23:00 | 2023-07-07 | 2023-07-07 23:00 | 2023-07-07 23:30 | 2023-07-07 23:30 | 2023-07-08 20:00 | 2023-07-08 23:00 | 2023-07-08 23:00 | 2023-07-09 23:30 | 2023-07-05 12:00 | 2023-07-06 23:00 | 2023-07-06 23:00 | 2023-07-07 | 2023-07-07 23:00 | 2023-07-07 23:30 | 2023-07-07 23:30 | 2023-07-08 20:00 | 2023-07-08 23:00 | 2023-07-08 23:00 | 2023-07-09 23:30
Undefined | Demob Final (ROV) | 2023-07-05 12:00 | 2023-07-06 23:00 | 2023-07-06 23:00 | 2023-07-07 | 2023-07-07 23:00 | 2023-07-07 23:30 | 2023-07-07 23:30 | 2023-07-08 20:00 | 2023-07-08 23:00 | 2023-07-08 23:00 | 2023-07-09 23:30 | 2023-07-06 12:00 | 2023-07-07 23:00 | 2023-07-07 23:00 | 2023-07-08 | 2023-07-08 23:00 | 2023-07-08 23:30 | 2023-07-08 23:30 | 2023-07-09 20:00 | 2023-07-09 23:00 | 2023-07-09 23:00 | 2023-07-10 23:30
Undefined | Milestone: Finish Survey | 2023-07-06 12:00 | 2023-07-07 23:00 | 2023-07-07 23:00 | 2023-07-08 | 2023-07-08 23:00 | 2023-07-08 23:30 | 2023-07-08 23:30 | 2023-07-09 20:00 | 2023-07-09 23:00 | 2023-07-09 23:00 | 2023-07-10 23:30 | 2023-07-06 12:00 | 2023-07-07 23:00 | 2023-07-07 23:00 | 2023-07-08 | 2023-07-08 23:00 | 2023-07-08 23:30 | 2023-07-08 23:30 | 2023-07-09 20:00 | 2023-07-09 23:00 | 2023-07-09 23:00 | 2023-07-10 23:30